## Mission Metrics
Apollo 11 Mission Metrics - demo data
Metric | Value | Plain-English meaning
Crew | 3 astronauts | Two landed; one stayed in lunar orbit to operate the return spacecraft.
Launch vehicle | Saturn V | The rocket powerful enough to send the crew toward the Moon.
Lunar surface stay | about 21.5 hours | Time Armstrong and Aldrin spent on the Moon before liftoff.
Moonwalk duration | about 2.5 hours | Time spent outside the Lunar Module on the surface.
Landing site | Sea of Tranquility | Chosen for a relatively smooth landing area, though the final approach still required judgment.
Return | Pacific splashdown | The mission goal included safe return, not only landing.

## Risk Register
Apollo 11 Risk Register - simplified for demo
Risk | Likelihood | Impact | Evidence / trigger | Mitigation | Demo lesson
Computer overload alarms during descent | Medium | High | 1201/1202 alarms | Mission Control had trained for alarm handling and confirmed guidance was still working. | Prepared teams can make fast decisions under pressure.
Unsafe landing terrain | Medium | High | Boulders near planned landing area | Armstrong manually flew to a safer area. | Human judgment complements automation.
Low descent fuel margin | Medium | High | Manual landing adjustment used additional time | Fuel monitoring and go/no-go discipline. | Time-boxed decisions need clear thresholds.
Ascent engine failure | Low | Critical | Single path home from lunar surface | Extensive testing and contingency planning. | Some risks have low probability but severe consequences.
Public communication pressure | High | Medium | Global live audience | Simple mission language and disciplined communications. | Clear storytelling matters in complex projects.