## Zava_Risk_Register
RiskId | Area | Risk | Impact | Probability | Owner | Mitigation | Status
R-01 | NFC activation | NFC tag activation capacity may delay final packing | High | Medium | Omar Haddad | Reserve evening activation slot; pre-stage Cobalt and Black runs first | Open
R-02 | Supply chain | White XL and XXL availability below demand buffer | High | High | Omar Haddad | Offer substitution rules; cap White XL/XXL mix; disclose risk to customer | Open
R-03 | Freight | Singapore hub has customs clearance uncertainty | Medium | Medium | Rafael Ortiz | Ship 48 hours earlier; use premium freight lane | Open
R-04 | Finance | Expedite fees can erode gross margin | High | Medium | Lena Vogt | Set pricefloor at or above EUR 25.80; approve exception only with COO sign-off | Open
R-05 | Customer comms | Overpromising before partner confirmation | High | Low | Maya Chen | Use conditional commitment language until partner capacity is locked | Open