# Teams Meeting Transcript

Meeting: Q2 Supply Chain Executive Planning

Date: May 13, 2026 | 10:00 AM - 11:15 AM

Attendees: Sarah Chen (Director), Marcus Johnson (Warehouse), David Reeves (Carriers), Lisa Rodriguez (Planning), Tom Williams (Finance)

## Meeting Transcript

10:00 AM
        Sarah Chen:

10:02 AM
        Lisa Rodriguez:

10:04 AM
        Tom Williams:

10:05 AM
        Lisa Rodriguez:

10:07 AM
        Sarah Chen:

10:08 AM
        Marcus Johnson:

10:10 AM
        Tom Williams:

10:11 AM
        Marcus Johnson:

10:12 AM
        Sarah Chen:

10:14 AM
        David Reeves:

10:17 AM
        Sarah Chen:

10:18 AM
        David Reeves:

10:20 AM
        Tom Williams:

10:21 AM
        David Reeves:

10:23 AM
        Sarah Chen:

10:25 AM
        Marcus Johnson:

10:26 AM
        Sarah Chen:

10:28 AM
        Lisa Rodriguez:

10:30 AM
        Sarah Chen:

10:31 AM
        Sarah Chen:

## Meeting Summary (AI-Generated)

Approved: 40 temporary warehouse staff for LATAM by mid-June ($80K budget)

Approved: Shift 15% carrier volume to backup providers (effective June 1) to negotiate better fuel surcharge rates; save $80-90K/month

Approved: Copilot AI route optimization pilot (2% North America volume) to improve routing efficiency

Approved: APAC best-practice knowledge-transfer session to scale efficiency to LATAM and North America

## Action Items

Marcus Johnson: Hire and onboard 40 temporary staff in São Paulo & Mexico City by June 10

David Reeves: Submit carrier renegotiation proposal and backup partner activation plan by May 25; activate backup carriers by June 1

Lisa Rodriguez: Schedule APAC knowledge-transfer meeting; launch Copilot route optimization pilot (2% volume) by May 20

Sarah Chen: Brief exec team on cost savings and efficiency gains; follow-up meeting May 27

Tom Williams: Approve budget: $80K LATAM staffing + carrier renegotiation costs

## Purpose:

Approved: 40 temporary warehouse staff for LATAM by mid-June ($80K budget)

Approved: Shift 15% carrier volume to backup providers (effective June 1) to negotiate better fuel surcharge rates; save $80-90K/month

Approved: Copilot AI route optimization pilot (2% North America volume) to improve routing efficiency

Approved: APAC best-practice knowledge-transfer session to scale efficiency to LATAM and North America

## Marcus Johnson:

Marcus Johnson: Hire and onboard 40 temporary staff in São Paulo & Mexico City by June 10

David Reeves: Submit carrier renegotiation proposal and backup partner activation plan by May 25; activate backup carriers by June 1

Lisa Rodriguez: Schedule APAC knowledge-transfer meeting; launch Copilot route optimization pilot (2% volume) by May 20

Sarah Chen: Brief exec team on cost savings and efficiency gains; follow-up meeting May 27

Tom Williams: Approve budget: $80K LATAM staffing + carrier renegotiation costs