# Zava Rush Order Standup Transcript

Date: 2026-06-02 13:30

Meeting: Rush Order Standup

Attendees: Zoe Keller, Maya Chen, Omar Haddad, Lena Vogt, Rafael Ortiz

# Transcript excerpt

Zoe Keller: We need one recommendation, not three options. The customer needs confidence by five.

Maya Chen: The customer explicitly said reliability matters more than lowest price. If we can be specific on constraints, I can position this as a premium launch package.

Omar Haddad: Inventory alone is short. Berlin can help with Cobalt fast. Porto can help with White, but XL and XXL are tight and customs timing for Singapore is not perfect.

Lena Vogt: The margin breaks if we accept discounts and eat expedite cost. My guardrail is EUR 25.80 minimum average unit price. Anything below that needs Zoe's approval.

Rafael Ortiz: Packing is manageable if we sequence by hub. Singapore needs the earliest freight cut. NFC activation is the part I want locked today.

Zoe Keller: Good. I want the response to say yes, but only with conditions. We should sound decisive, not defensive.

# Action items heard in meeting

Omar: confirm partner capacity by 15:30.

Lena: validate pricefloor by 16:00.

Rafael: confirm Singapore premium freight cut-off by 16:00.

Maya: draft customer response by 16:30.

Zoe: approve final recommendation before 17:00.