## Risk Register
Contoso SmartRetail Tablet S1 — Launch Risk Register
Maintained by: Programme Management Office · Updated: 28 March 2026
Risk ID | Category | Risk Description | Likelihood (1-5) | Impact (1-5) | Risk Score | Mitigation | Owner | Status
R-01 | Technical | SAP connector not ready by GA launch date — blocks inventory data access in Copilot for Northwind Traders | 4 | 4 | 16 | Engage Contoso PS team immediately; parallel-track connector dev with customer IT; set interim manual workaround (CSV export) | Tom Brandt (Contoso PS) | OPEN — HIGH
R-02 | Legal/Compliance | GDPR DPA addendum review takes longer than 3 weeks — delays Fabrikam Fashion sign-off | 3 | 4 | 12 | Provide pre-signed DPA template; escalate to Microsoft legal for priority review; prepare alternative contract structure | Sara Novak (AE) | IN PROGRESS
R-03 | Budget | Adventure Works CFO does not approve Copilot license uplift — limits deployment to F3 only | 3 | 4 | 12 | Prepare ROI model with specific AW headcount data; schedule CFO briefing; explore phased license roll-out | Sara Novak (AE) | IN PROGRESS
R-04 | Adoption | Associates 50+ require extended onboarding — slows deployment velocity | 4 | 3 | 12 | Develop simplified 15-min video onboarding (in progress); partner with Northwind L&D team; pilot buddy system | James Fletcher (CSM) | IN PROGRESS
R-05 | Competitive | Zebra ET45 shortlisted by Northwind IT Director — risk of split decision | 3 | 3 | 9 | Arrange hands-on comparison session; prepare TCO model at 3-year horizon; engage Northwind CIO directly | Sara Novak (AE) | OPEN — MEDIUM
R-06 | Technical | Wi-Fi configuration issues in older store locations (week 2 incident) | 2 | 3 | 6 | Pre-deploy Intune Wi-Fi profile template; include site survey in standard onboarding; document resolution playbook | Tom Brandt (Contoso PS) | RESOLVED
R-07 | Licensing | Seasonal/contract worker licensing model unclear — may delay Adventure Works decision | 3 | 2 | 6 | Escalate to Microsoft licensing team for formal guidance; prepare two licensing scenarios for customer | Sara Novak (AE) | OPEN — MEDIUM
R-08 | Security | Customer requests pen test results — Contoso does not have current external pen test report | 2 | 3 | 6 | Commission external pen test (Q2); provide Microsoft Secure Score and Defender for Endpoint documentation as interim | Contoso Security Team | OPEN — LOW
R-09 | Supply Chain | Device delivery lead time may extend to 10 weeks for orders above 500 units | 2 | 2 | 4 | Reserve inventory block for top 3 accounts; communicate lead time expectations proactively | Contoso Operations | MONITORING
R-10 | Market | Competitor announcement (Samsung / Zebra) during our pilot window — shifts customer attention | 2 | 2 | 4 | Prepare competitive battlecard update; monitor announcements weekly; brief account teams within 24h of any news | Contoso Product Marketing | MONITORING
Legend: | High Risk (12-25) | Medium Risk (6-9) | Low Risk (1-4)