Zava Rush Order Operations Plan

Decision-ready plan for Microsoft Events AI Launch Summit order

# Executive Recommendation

Proceed with a conditional yes. Zava can commit to the 20,000-unit rush order if partner capacity, NFC activation, pricefloor, and premium freight are confirmed before the customer response deadline.

# Four-Hour Action Plan

| Workstream | Owner | Deadline | Outcome |
| --- | --- | --- | --- |
| Partner capacity | Omar Haddad | 15:30 | Berlin and Porto capacity locked |
| Pricing | Lena Vogt | 16:00 | EUR 25.80 pricefloor confirmed |
| Freight | Rafael Ortiz | 16:00 | Singapore premium lane confirmed |
| Customer response | Maya Chen | 16:30 | Conditional yes drafted |
| Executive approval | Zoe Keller | 17:00 | Final recommendation approved |

# Risks and Mitigations

White XL/XXL supply is the highest visible customer risk; offer substitution rules and disclose the constraint.

NFC activation is the operational bottleneck; reserve evening capacity and sequence Black/Cobalt first.

Expedite fees can erode margin; keep the average unit price at or above EUR 25.80.

Singapore customs timing needs premium freight and earlier packing cut-off.

# Customer Message Guidance

Tone: confident, transparent, and commercially disciplined. Do not expose internal cost details. Use conditional commitment language until partner confirmations are complete.